## Sheet2
Sort Order | Date for Change | Include in Summer Updates? | Current System | Future Status | Details of Change | Lock Out Date | Re-Open Date | What happens on July 1, 2018? | What happens on January 1, 2019? | What happens on July 1, 2019? | What happens with the Historical Data? | When can the system be decommissioned? | Reviewer for Posting | Approved for posting | Functional Contact | Technical Contact
1 | 2018-01-01 | No | Vehicle Rental Website (cars.uga.edu) | Complete | Replaced by FMD AIM Functionality | N/A | N/A | N/A | N/A | N/A | Vehicle Rental Website DB2 data will be archived in the data warehouse on August 1, 2019. | The Vehicle Rental Website was decommissioned in May 2018.
2 | 7/1/2018 | No | EJV (ejv.uga.edu) | Retire | Replaced by PeopleSoft Financial General Ledger Journal | Lock Out Date: July 10, 2018 Users will not be able to access EJV on July 10, 2018. | Re-Open in Read-Only Mode Date: July 16, 2018 EJV will re-open on July 16, 2018 and will remain in read-only mode until July 1, 2019. | EJV can be accessed until the lockout date on July 10, 2018. It will re-open on July 16, 2018 in read-only mode. | EJV will be available in read-only mode. | Users will no longer have access to EJV starting July 1, 2019. | EJV DB2 data will be archived in the data warehouse on August 1, 2019. Note: There are attachments in the database. | EJV will be decommisisoned on September 1, 2019.
3 | 7/1/2018 | No | eTravel Authority (echeck.uga.edu) | Retire | Replaced by PeopleSoft Travel and Expenses | Lock Out Date: June 27, 2018 Users will not be able to make updates to eTravel Authority starting on on June 27, 2018. | Re-Open in Read-Only Mode Date: July 27, 2018. eTravel Authority will switch to read-only mode starting on July 27, 2018 and will remain in read-only mode until July 1, 2019. | eTravel Authority will be available in read-only mode. | eTravel Authority will be available in read-only mode. | Users will no longer have ccess to eTravel Authority starting July 1, 2019. | eTravel Authority DB2 data will be archived in the data warehouse on August 1, 2019. | eTravel Authority will be decommisisoned on September 1, 2019.
4 | 7/1/2018 | No | Vendor Database (vendors.uga.edu) | Retire | Replaced by PeopleSoft Purchasing - Suppliers | Lock Out Date: June 27, 2018 Users will not be able to make updates to the Vendor Database starting on June 27, 2018. | Re-Open in Read-Only Mode Date: July 27, 2018. The Vendor Database will switch to read-only mode starting on July 27, 2018 and will remain in read-only mode until until July 1, 2019. | The Vendor Database will be available in read-only mode. | The Vendor Database will be available in read-only mode. | Users will no longer have access to the Vendor Database starting July 1, 2019. | Vendor Database DB2 data will be archived in the data warehouse on August 1, 2019. | The Vendor Database will be decommissioned on September 1, 2019.
5 | 7/1/2018 | No | eCheck (echeck.uga.edu) | Retire | Replaced by PeopleSoft Travel and Expenses, and Accounts Payable | Lock Out Date: June 27, 2018 Users will not be able to make updates to eCheck starting on June 27, 2018. | Re-Open in Read-Only Mode Date: June 27, 2018. eCheck will switch to read-only mode starting on June 27, 2018 and will remain in read-only mode until July 1, 2019. | eCheck will be available in read-only mode. | eCheck will be available in read-only mode. | Users will no longer have access to eCheck starting July 1, 2019. | eCheck DB2 data will be archived in the data warehouse on August 1, 2019. Note: There are attachments in the database. AP will go to Fortis for attachments. | eCheck will be decommissioned on September 1, 2019.
6 | 7/1/2018 | No | WebDFS (Budget Amendments) (webdfs.uga.edu) | Retire | Budget Amendments Replaced by PeopleSoft Financials Commitment Control Budget Journal/Transfer and Hyperion starting July 1, 2018. Personnel documents replaced by OneUSG Connect functionality in January 2019. | Lock Out Date: March 31, 2019 Users will complete budget amendments in WebDFS through June 15, 2018. Any budget amendments entered after June 15, 2018 will not be processed. Users will begin using PS Financials to process budget journals starting July 2, 2018. | N/A | Budget Amendments will be completed in the UGA Budget Management System (Hyperion). Users will continue using WebDFS to process personnel documents between July 2, 2018 and December 15, 2018. Any personnel documents entered after December 15, 2018 will not be processed. | Budget Amendments will be completed in the UGA Budget Management System (Hyperion). Users will continue using WebDFS to process personnel documents between July 2, 2018 and December 15, 2018. Any personnel documents entered after December 15, 2018 will not be processed. | User will no longer have access to WebDFS after April 2019. | WebDFS Budget Amendments DB2 data will be archived in the data warehouse on August 1, 2019. | This informaiton will be available summer 2018.
7 | 7/1/2018 | No | WebDFS (Budget Development) (webdfs.uga.edu) | Retire | Replaced by Hyperion | Lock Out Date: End of May 2018 Users will not be able to access WebDFS Budget Development starting at the end of May 2018. | Re-Open Date: Late July WebDFS Budget Development will re-open in late July. This system will be open for reporting only thorugh January 1, 2019. | Users will use the UGA Budget Management System (Hyperion). WebDFS Budget Development will be open for reporting only through Janaury 1, 2019. | Users will use the UGA Budget Managemnet System (Hyperion). Users will no longer have access to WebDFS Budget Development after Janaury 1, 2019. | Users will no longer have access to WebDFS Budget Development after January 1, 2019. | WebDFS Budget Development DB2 data will be archived in the data warehouse on August 1, 2019. | WebDFS Budget Development will be decommissioned on September 1, 2019.
8 | 7/1/2018 | No | WebDFS Accounting (webdfs.uga.edu) | Retire | Replaced by PeopleSoft Financials for budget and actual transactions. Pending item functionality will be evaluated and developed as a OneSource feature release. | Lock Out Date: Fall 2018 (specific date TBD) Accounting data will no longer be updated in WebDFS Accounting starting July 1, 2018. | N/A | Accounting data will no longer be updated in WebDFS Accounting starting July 1, 2018. | N/A | Users will no longer have access to WebDFS Accounting starting July 31, 2019. Data will be archived per record retention requirements. | WebDFS Accounting DB2 data will be archived in the data warehouse on August 1, 2019. | WebDFS Accounting will be decomissioned August 1, 2019.
9 | 7/1/2018 | No | ETicket (eticket.uga.edu) | Retire | Replaced by PeopleSoft Financials General Ledger Journal | Lock Out Date: June 28, 2018 Users will not be able to access eTicket on June 28, 2018. | Re-Open Date: July 16, 2018 eTicket will re-open on July 16, 2018 and will remain in read-only mode until July 1, 2019. | eTicket can be accessed until the lockout date on June 28, 2018. It will reopen in read-only mode on July 16, 2018. | eTicket will be available in read-only mode. | Users will no longer have access to eTIcket starting July 1, 2019. | eTicket DB2 data will be archived in the data warehouse on August 1, 2019. Note: There are attachments in the database. | eTicket will be decommissioned on September 1, 2019.
10 | 2018-07-01 | No | Core Cashiering | Replace | Replaced by Touchnet | Lock Out Date: June 27, 2018 @ 11:00 a.m. | TouchNet will re-open on July 1, 2018. | TouchNet will be used for departments to make all deposits. | TouchNet will remain available. | TouchNet will remain available. | Core Cashiering will remain available for query access. | Core Cashiering will be decommissioned in August 2019.
11 | 2018-07-01 | No | Credit Card Web Deposit Transmittal System | Replace | Replaced by Touchnet | Lock Out Date: June 27, 2018 @ 12:00 p.m. | TouchNet will re-open on July 1, 2018. | TouchNet will be used for departments to make all deposits | TouchNet will remain available. | TouchNet will remain available. | The Credit Card Web Deposit Transmittal System will remain available to the Centeral Offices for query access. | Credit Card Web Deposit Transmittal System will be decommissioned in August 2019.
12 | 2018-07-01 | No | UGAMart (ugamart.uga.edu) | Retrofit | A new chart of accounts will be added | Lock Out Date: June 26, 2018 - July 8, 2018 Users will not be able to access UGAMart from June 26, 2018 through July 8, 2018. | Re-Open Date: July 9, 2018 Users wil be able to access UGAMart again starting June 9, 2018. | UGAMart can be accessed until the lockout date on June 26, 2018. It will reopen on July 9, 2018. | UGAMart will remain avaialble. | UGAMart will remain available. | UGAMart DB2 data will be archived in the data warehouse on August 1, 2019. Historical data will be available in UGAMart. | N/A, this system will not be decommissioned.
13 | 2018-07-01 | No | Works (payment2.works.com) | Retrofit | A new chart of accounts will be added. Credit card transactions can continue during lock-out period. | Lock Out Date: June 27, 2018 - July 8, 2018 Users will not be able to access Works from June 27, 2018 through July 8, 2018. | Re-Open Date: July 9, 2018 Users will be able to access Works again starting July 9, 2018. | Works can be accessed until the lockout date on June 27, 2018. It will reopen on July 9, 2018. | Works will remain avaialble. | Works will remain avaialble. | Historical data will remain available in Works. | N/A, this system will not be decommissioned.
14 | 2018-07-01 | No | Work Order Request (workrequest.fmd.uga.edu) | Retrofit | A new chart of accounts will be added | N/A | N/A | Work Order Request will use the new chart of accounts. | N/A | N/A | Historical Work Order Request data will be available in AIM. | N/A, this system will not be decommissioned.
15 | 2018-07-01 | No | EPAR (Phase I) (epar.uga.edu) | Retire | Replaced by Sponsored Projects reporting Effort Certification replaced with Sponsored Project Report | Lock Out Date: July 4, 2018 Users will not be able to access EPAR starting July 4, 2018. | Re-Open Date: July 30, 2018 EPAR will re-open on July 30th to use for payroll adjustments. | PARs will no longer require certification. Email notifications about PAR certifications will be turned off. EPAR system will be available for payroll adjustments. | Users will have read-only access to EPAR after December 11, 2018. | Users will no longer have access to EPAR after July 1, 2019. | EPAR DB2 data will be archived in the data warehouse on August 1, 2019. | EPAR will be decommissioned on September 1, 2019.
16 | 2018-07-01 | No | RUSS (russhelp.uga.edu) | Retire | Replaced by PeopleSoft Asset Management | Lock Out Date: July 9, 2018 Users will not be able to access RUSS starting July 9, 2018. | N/A | Users will no longer have access RUSS after July 9, 2018. RUSS data will be available in Simpler. | Users will no longer have access to RUSS after July 9, 2018. | Users will no longer have access to RUSS after July 9, 2018. | RUSS DB2 data will be archived in the data warehouse on August 1, 2019. | RUSS will be decommissioned on August 1, 2018.
17 | 2018-07-01 | No | Simpler (simpler.uga.edu) | Retrofit | New PeopleSoft Financials reports will be added | N/A | N/A | PeopleSoft Financials data will be added to Simpler. | OneUSG Connect data will be added to Simpler. | Simpler will remain available. | TBD | N/A, this system will not be decommissioned.
18 | 2018-07-01 | No | FIDB (Facilities Database) | Retire | Replace by Data Warehouse | N/A | N/A | Facilities database data will be available in the data warehouse with PeopleSoft Finance department numbers. The Facilitites database on the maifnrame will still be available, but will not include the PeopleSoft Finance department numbers. | Facilities data will be available in the data warehouse with PeopleSoft Finance department numbers. The Facilities database on the maifnrame will be decommissioned in January 2019. | Users will no longer have access to the Facilities Database starting January 2019. | Historical Facilities Database data will be available in AIM. Facilities data from AIM will be available in the reportable data warehouse starting July 1, 2018. | The Facilities Database will be decommissioned in January 2019.
19 | 2018-07-01 | No | Telphone Billing, Reporting, and E911 | Retrofit | Following changes will occur: Billing/Reporting information will be updated with new chart of account information. The system will move to a new cloud-hosted solution with a new look and feel. Logins to the system will now require your MyID and ArchPass DUO. | Lock Out Date: June 15, 2018 Users will not be able to access Telephone Billing on June 15, 2018. | Re-Open Date: September 1, 2018 Telephone Billing will re-open on Septmeber 1, 2018. | System will go live in the cloud-hosted environment. Telephone Services will convert account strings and provision access. The system will be read-only through re-open date, but data in the system will be dynamic while adjustments are made in the system. | N/A | N/A | Historical telephone reports will be avialable in the telephone system. | The old system will be decommissioned on November 1, 2018 after Telephone Services has run in the new cloud-hosted service for 4 months.
20 | 2019-01-01 | Yes | eLeave and Leave Forms (eleave.uga.edu) | Retire | Replaced by HCM Time and Attendence | Lock Out Date: December 15, 2018 Users will not be able to submit leave requests through eLeave starting December 16, 2018. | Re-Open Date in Read-Only Mode: December 16, 2018 eLeave will switch to read-only mode starting December 16, 2018 and will remain in read-only mode through July 1, 2019. | N/A | Users will use utilize the absence management and time and labor system available in OneUSG Connect to request and/or approve leave. eLeave will be available in read-only mode until July 1, 2019. | Access to eleave will be revoked on July 1, 2019. | eLeave DB2 data will be archived in the data warehouse on August 1, 2019. | eLeave will be decommissioned on September 1, 2019. | Baleigh Barnes | 2018-09-04 | Lindsey Van Note | Russell Hatfield
21 | 2019-01-01 | Yes | WebDFS (Personnels) (webdfs.uga.edu) | Retire | Replaced by HCM Payroll | Lock Out Date: November 30, 2018. WebDFS Personnels must be submitted to the Budget Office by November 30, 2018 so that these records are included in the data conversion to OneUSG Connect. After November 30, 2018 emergency requests can be submitted until December 20, 2018. These records will not be included in the data conversion to OneUSG Connect and will need to be entered manually into the new system. Details of emergency procedures will be shared by October 1, 2018. | WebDFS Peronnels will not be re-opened to campus after December 20, 2018. Central Offices will retain access to WebDFS Personnels from December 20, 2018 to February 28, 2019. | N/A | Personnels will be completed in OneUSG Connect. Users will be able to view historical Personnel data in the Data Warehouse. | Users will no longer have access to WebDFS Personnels starting February 28, 2019. | If users need access to historical WebDFS Personnel information after December 20, 2018, they should submit a reqeust to the Budget Office. Users will have access to historical WebDFS Personnel information in the data warehouse starting March 1, 2019. | WebDFS Personnels will be decomissioned on March 1, 2019. | Chris Allinger | 2018-08-31 | Chris Allinger | Kenneth Little
22 | 2019-01-01 | Yes | Kronos and Kronos Time Clocks (mytime.uga.edu) | Retire | Replaced by HCM Time and Labor and Kaba Time Clocks | Last Timesheets in Kronos: Hourly pay period December 6, 2018 through December 15, 2018 is due December 17, 2018 at 9:00am. Salaried pay period December 13, 2018 through December 15, 2018 is due December 18, 2018 at 9:00am. Lock Out Date for Kronos December 20, 2018. The last timesheets in Kronos are due on December 18, 2018 at 9:00am. Users will not be able to access Kronos after December 16, 2018. Supervisors will have access to Kronos through December 20, 2018 to process the final Kronos payroll. After December 20, 2018, only the Central Payroll Office will have access to Kronos. The last day to use Kronos Timeclocks will be December 15, 2018. Employees who work overnight on December 15, 2018 will also clock out from Kronos on December 16, 2018. December 16, 2018 will be the first day to use Kaba Clocks and the PeopleSoft Web Clock. | Kronos will not be re-opened to campus after December 20, 2018. Unit Approvers and central offices will have read only access to Kronos starting December 22, 2018 through March 1, 2019. | N/A | Users will start using Kaba on December 16, 2018. Unit Approvers and central offices will have read only access to Kronos starting December 22, 2018 through March 1, 2019. | Kronos will be decommissioned in March 2019. Users will no longer have access to Kronos starting March 2019. | Portions of the Kronos database (timesheets, punches, etc.) will be archived in the data warehouse in March 2019. | Kronos will be decommissioned in March 2019. | Amanda Ganger | 2018-08-27 | Amanda Ganger | Russell Hatfield
24 | 2019-01-01 | Yes | Faculty Information Records System (FIRST) (first.uga.edu) | Retire | Replaced by UGAJobs and HCM | Lock Out Date: December 5, 2018 Users will not be able to access FIRST after December 5, 2018. | N/A. FIRST will not re-open to campus. On December 16, 2018, the Office of Faculty Affairs will have access to FIRST in read-only mode until July 1, 2019. Starting December 16, 2018, users who need access to FIRST data can submit a data access request on the Data Warehouse website. Faculty data from FIRST will also be accessible through OneUSG after December 16, 2018. | Starting December 16, 2018, FIRST and the Faculty Database will be the authoritative sources for historical faculty data. Users who need access to this data can submit a data access request to on the Data Warehouse website. Active faculty data from FIRST and the Faculty Database will be accessible through OneUSG and the Data Warehouse after December 16, 2018. New entries for faculty should be entered into OneUSG Connect and UGAJobs. | New entries for faculty should be entered into OneUSG Connect and UGAJobs. | Users will no longer have access to FIRST starting July 1, 2019. | Historical faculty data will be available in the data warehouse on March 1, 2019. The Data Warehouse will be the authoritative source for historical faculty data at this time. | FIRST will be decommissioned on July 1, 2019. | Sarah Covert | 2018-08-31 | Sarah Covert | David Crouch
25 | 2019-01-01 | Yes | Identity Management Tool used for UGAID Creation (URL available upon request) | Retrofit | Integrations with HCM | Lock Out Date for Manual Identity Creation: December 7, 2018 Identity creation processes used by the Payroll Office, the Office for the VP of Research, and the UGACard Office will no longer be available. New identity records cannot be created via these processes after December 7, 2018. Units that previously had create and update access to the IDM tools will be converted to search/read-only access on December 7, 2018. | Re-Open Date: December 7, 2018 (for search functionality only) Users will have access to the IDM Search Tools. UGA HR and Payroll employees will no longer have access to create identities in IDM. Identity records previously created through this process will be created through OneUSG Connect business processes. Units that previously had create and update access to the IDM tools will be converted to search/read-only access on December 7, 2018. | The IDM tools will remain available to campus. | Users will have access to the IDM Search Tools. Users will also have access to conduct employee searches in the data warehouse. | Users will have access to the IDM Search Tools. Users will also have access to conduct employee searches in the data warehouse. | Historical data will be available in IDM. | N/A, this system will not be decommissioned. | Shannon Marable | 2018-08-31 | Shannon Marable | Kristi Wall
26 | 2019-01-01 | Yes | UGAJobs (PeopleAdmin) (https://www.ugajobsearch.com) | Retrofit | Integrations with HCM | October 1, 2018 is the deadline for submitting the following in UGAJobs: - new faculty postings - faculty hiring proposals with a start date between November 1, 2018 and January 31, 2019 - staff position evaluations November 1, 2018 is the deadline for submitting the following in UGAJobs: - new staff postings - staff hiring proposals - faculty and staff position modifications Lock Out Date: November 14, 2018. Users will not be able to access UGAJobs on November 14, 2018. Instructions for emergency hire procedures for positions with November, December or January start dates will be available October 1, 2018. | Re-Open Date: December 16, 2018 Users will be able to access UGAJobs on December 16, 2018. Details for posting jobs: - New postings will be accepted - Old postings may be republished. - Applicants can access the system and apply for jobs Details for hiring proposals: - New proposals can be created and submitted - Faculty hiring proposals with February 2019 start dates should be submitted on this date Details for position management: - position modificationscan be created and submitted. | N/A | Users will continue to use UGAJobs. | Users will continue to use UGAJobs | For the foreseeable future, historical UGAJobs data will remain in UGAJobs. A longterm strategy is currently being determined. | N/A, this system will not be decommissioned. | Lindsey Van Note, Sarah Covert | 2018-08-31 | Lindsey Van Note
27 | 2019-01-01 | Yes | Faculty Database (FDB) | Retire | Replaced by HCM Faculty Events, Data Repository | Lock Out Date: December 5, 2018 Users will not be able to access the Faculty Database after December 5, 2018. | N/A. The Faculty Database will not re-open to campus. Beginning December 16, 2018, the Office of Faculty Affairs and the Office of Institutional Research will have access to the Faculty Database until July 1, 2019. The Faculty Database will be the authoritative source for historical faculty data. Users who need access to this data can submit a data access request on the Data Warehouse website. Faculty data from the Faculty Database also will be accessible through UGA Elements, and OneUSG after December 16, 2018. | Starting December 16, 2018, FIRST and the Faculty Database will be the authoritative source for histoircal faculty data. Users who need access to this data can submit a data access request to on the Data Warehouse website. Active faculty data from FIRST and the Faculty Database will be accessible through OneUSG and the Data Warehouse after December 16, 2018. New entries for faculty should be entered into OneUSG Connect and UGAJobs. | New entries for faculty should be entered into OneUSG Connect and UGAJobs. | Users will no longer have access to the Faculty Database starting July 1, 2019. | Historical faculty data will be available in the data warehouse on March 1, 2019. The Data Warehouse will be the authoritative source for historical faculty data at this time. | The Faculty Database will be decommissioned on July 1, 2019. | Paul Klute | 2018-08-31 | Paul Klute | Tracie Sapp
28 | 2019-01-01 | Yes | UGA Elements (elements.uga.edu) | Retrofit | Integrations with HCM | N/A | N/A | N/A | Users will continue to use UGA Elements. | Users will continue to use UGA Elements. | Historical data will remain in UGA Elements. | N/A, this system will not be decommissioned. | Bob Scott | 2018-08-27 | Bob Scott | David Crouch
29 | 2019-01-01 | Yes | EPAR (Phase II) (epar.uga.edu) | Retire | Replaced by Sponsored Projects Report | Lock Out Date: December 11, 2018 Users will not be able to access EPAR on December 11, 2018. | Users will have read-only access to EPAR after December 11, 2018. | PARs will no longer require certification. Users will no longer receive email notifications about PAR certifications. EPAR will be available for payroll adjustments. | Users will have read-only access to EPAR after December 11, 2018. | Users will no longer have access to EPAR after July 1, 2019. | EPAR DB2 data will be archived in the data warehouse on August 1, 2019. | EPAR will be decommissioned on September 1, 2019. | Shawn Hill | 2018-08-24 | Shawn Hill | Lauren Holomb
30 | 2019-01-01 | Yes | Arrow (arrow.uga.edu) | Retire | Replaced by various reporting tools, reports sourced from PeopleSoft Financials, and reports sourced from OneUSG Connect. | N/A | N/A | N/A | Users will no longer have access to Arrow starting December 2018. | Users will no longer have access to Arrow starting December 2018. | Historical data will be available through other reporting tools. | Arrow will be decommissioned on February 1, 2019. | Russell Hatfield |  | Holley Schramski, Sharon Logan | Russell Hatfield
31 | 2019-01-01 | Yes | Campaign for Charities (charities.uga.edu) | Retire | Replaced by OneUSG Connect | Lock Out Date: December 7, 2018 December 7, 2018 is the dealine to submit contributions online. Users will be able to access Campaign for Charities in read-only mode after December 7, 2018 to view their information. Paper forms can still be submitted to the Bugdet Office. | Users will be able to access Campaign for Charities in read-only mode after December 7, 2018 until July 1, 2019. | N/A | Users will be able to access Campaign for Charities in read-only mode after December 7, 2018 until July 1, 2019. Users will submit updates and new contributions through OneUSG Connect in 2019. Timelines and procedures are currently being determined. | Users will no longer be able to access the legacy Campaign for Charities system. | Campaign for Charities DB2 data will be archived in the data warehouse on July 1, 2019. | Campaign for Charities will be decommissioned on July 1, 2019. | Chris Allinger | 2018-08-31 | Chris Allinger | Kenneth Little
32 | 2019-07-01 | No | QMF | Retire | Replaced by queries sourced from PeopleSoft Financials and HCM. | N/A | N/A | Financial queries will be run within PeopleSoft. Finance data other than payroll related charges will not be current. HR data will remain current. | Financial queries will be run within PeopleSoft. HR queries will be run with the data warehouse. | Users will no longer have access to QMF starting July 1, 2019. | N/A, this is a querying tool. | QMF will be decommissioned in December 2019.
33 | 2019-07-01 | No | IMS (also known as TSO, Mainframe green screens) | Retire | Financial IMS Applications will be replaced by PeopleSoft Finance; HR IMS Applciations will be replaced by OneUSG Connect. | N/A | N/A | Users will transition to read-only access in IMS based on dates that other systems transition to read-only mode. | Users will transition to read-only access in IMS based on dates that other systems transition to read-only mode. | Users will no longer have access to IMS starting July 1, 2019. | Historical data will be available through other reporting tools. | IMS will be decommissioned in December 2019.
34 | 2019-07-01 | Yes | Employee.uga.edu | Retain | employee.uga.edu will only include functionality for displaying historical checkstubs and W2's. | N/A. Certain functionality will be removed with the OneUSG Connect go-live. | N/A. Certain functionality will be removed with the OneUSG Connect go-live. | N/A | Starting January 1, 2019, users will be able to view the following on Employee Self-Service: - My Paychecks, dating back to 2010 - My W-2's, dating back to 2007 - My Leave Balances, from January 1 through December 31, 2018 Starting January 1, 2019, users will no longer be able to view the following on Employee Self-Service: - My Home Address (replaced with OneUSG Connect) - My Addresses (replaced with OneUSG Connect) - My Personnel Data (replaced with OneUSG Connect) - My Workbench (replaced with OneUSG Connect) - Training and Development Class Registration Request (replaced with the new Training & Development System) | Starting January 1, 2019, users will be able to view the following on Employee Self-Service: - My Paychecks, dating back to 2010 - My W-2's, dating back to 2007 My Leave Balances functionality will be removed and historical data will no longer be displayed. | employee.uga.edu DB2 data will be archived in the data warehouse on August 1, 2019. | This informaiton will be available Spring 2019. | Russell Hatfield |  | Sharon Logan | Russell Hatfield
35 | 2019-07-01 | Yes | IMS password change (https://tso.cc.uga.edu/chpwform.html) | Retire | Replaced by MyID Password Change | Lock Out Date: July 1, 2019 Users will no longer have RACFID (IMS, TSO, Mainframe) accounts after July 1, 2019. Users will not have access to their accounts to be able to change their IMS password starting July 1, 2019. | N/A. | IMS Password Changes will be available until July 1, 2019. | IMS Password Changes will be available until July 1, 2019. | IMS Password Changes will no longer be available after July 1, 2019. | N/A, no historical data will be kept. | The IMS Password change system will be decommissioned on July 1, 2019. | Shannon Marable |  | Shannon Marable | Gary Pittman
36 | 2019-01-01 | Yes | UGA Financial Management System (PeopleSoft Financials) | Retain | N/A | N/A The UGA Financial Management System will have a maintenance period of December 14-15, 2018 in preparation for the OneUSG Connect go-live. | N/A The UGA Financial Management System will have a maintenance period of December 14-15, 2018 in preparation for the OneUSG Connect go-live. | N/A | Users will continue to use the UGA Financial Management System. | Users will continue to use the UGA Financial Management System. | N/A | N/A, this system will not be decommissioned. | Russell Hatfield |  | Holley Schramski, Sharon Logan | Russell Hatfield
37 | 2019-01-01 | Yes | UGA Budget Management System (Hyperion) | Retain | N/A | N/A The UGA Budget Management System will have a maintenance period of December 14-15, 2018 in preparation for the OneUSG Connect go-live. | N/A The UGA Budget Management System will have a maintenance period of December 14-15, 2018 in preparation for the OneUSG Connect go-live. | N/A | Users will continue to use the UGA Budget Management System. | Users will continue to use the UGA Budget Management System. | N/A | N/A, this system will not be decommissioned. | Russell Hatfield |  | Holley Schramski, Sharon Logan | Russell Hatfield
38 | 2019-01-01 | Yes | Data Warehouse | Retain | N/A | N/A | N/A | N/A | The Data Warehouse will have data that was included in the conversion to OneUSG Connect. | Numerous legacy systems will have their historical data archived in the data warehouse by July 1, 2019. | Numerous legacy systems will have their historical data archived in the data warehouse by July 1, 2019. | N/A, this system will not be decommissioned. | Paul Klute |  | Paul Klute | Lori Slay

## Sheet1
Sort Order | Date for Change | Current System | Future Status | Details of Change | Lock Out Date | Re-Open Date | What happens on July 1, 2018? | What happens on January 1, 2019? | What happens on July 1, 2019? | What happens with the Historical Data? | When can the system be decommissioned?
6 | 7/1/2018 | WebDFS (Budget Amendments) (webdfs.uga.edu) | Retire | Replaced by PeopleSoft Financials Commitment Control Budget Journal/Transfer and Hyperion |  |  | Budget Amendments will be completed in the UGA Budget Management System (Hyperion). | Budget Amendments will be completed in the UGA Budget Management System (Hyperion). | Users will no longer have access to WebDFS Budget Amendments after April 2019. | WebDFS Budget Amendments DB2 data will be archived in the data warehouse on August 1, 2019. | This informaiton will be available summer 2018.
7 | 7/1/2018 | WebDFS (Budget Development) (webdfs.uga.edu) | Retire | Replaced by Hyperion | Lock Out Date: End of May 2018 Users will not be able to access WebDFS Budget Development starting at the end of May 2018 (year end dates TBD). | Re-Open Date: Late July WebDFS Budget Development will re-open in late July. This system will be open for reporting only thorugh January 1, 2019. | Users will use the UGA Budget Management System (Hyperion). WebDFS Budget Development will be open for reporting only through Janaury 1, 2019. | Users will use the UGA Budget Managemnet System (Hyperion). Users will no longer have access to WebDFS Budget Development after Janaury 1, 2019. | Users will no longer have access to WebDFS Budget Development. | WebDFS Budget Development DB2 data will be archived in the data warehouse on August 1, 2019. | WebDFS Budget Development will be decommissioned on September 1, 2019.
8 | 7/1/2018 | WebDFS Accounting (webdfs.uga.edu) | Retire | Replaced by PeopleSoft Financials |  |  | Users will use the UGA Budget Management System (Hyperion). Accounting data will no longer be updated in WebDFS Accounting starting July 1, 2018. | Users will use the UGA Budget Management System (Hyperion). Users will no longer have access to WebDFS Accounting starting fall 2018 (dates TBD summer 2018). | Users will no longer have access to WebDFS Accounting starting fall 2018 (dates TBD summer 2018). | WebDFS Accounting DB2 data will be archived in the data warehouse on August 1, 2019. | This informaiton will be available summer 2018.
21 | 2019-01-01 | WebDFS (Personnels) (webdfs.uga.edu) | Retire | Replaced by HCM Payroll | This information will be available summer 2018. | This information will be available summer 2018. | This information will be available summer 2018. Proposed information (confirm in June): Personnels will continue to be completed in WebDFS through January 1, 2019. | Proposed information (confirm in June): Personnels will be completed in OneUSG Connect starting January 1, 2019. Users will be able to view Personnels in WebDFS after the OneUSG Connect Go-Live on January 1, 2019. | Proposed information (confirm in June): Users will no longer have access to WebDFS Personnels after April 2019. | Proposed information (confirm in June): Users will have access to historical WebDFS Personnel information in March 2019. A solution will be deteremined summer 2018. | This informaiton will be available summer 2018.